## Slide 1
PROGRAM STATUS REVIEW · Q2 – Q4
Enterprise Data Platform
Framework Development & Business Goal Development
Bronze
Silver
Gold
Northwest Bank

## Slide 2
PROGRAM STATUS · EXECUTIVE DASHBOARD
Framework Development leads at 48%; Business Goal Development is underway at 20%
Framework Development
Chart: 
| Complete | Remaining
Framework Development | 48 | 52
48%
COMPLETE
Targeted completion
End of Q3
Business Goal Development
Chart: 
| Complete | Remaining
Business Goal Development | 20 | 80
20%
COMPLETE
Runs through end of Q4
3 sub-projects in flight

## Slide 3
PROGRAM ROADMAP · Q2 – Q4
Framework Development completes in Q3; Business Goal Development extends through Q4
Q2
Q3
Q4
Framework Development
Business Goal Development
Credit Admin Data & Reporting
Customer 360
Archer V1
Framework Development
Business Goal Development
Sub-project

## Slide 4
01
Framework Development
The reusable data factory — ingestion, transformation, governance, delivery
48%
overall complete
13
frameworks
Q3
target

## Slide 5
FRAMEWORK DEVELOPMENT · PROGRAM BOARD
Thirteen frameworks: four complete, six in progress, three not started
TARGET COMPLETION
End of Q3
COMPLETE 4
Landing Layer Framework
✓ Complete
Metadata Framework — Bronze
✓ Complete
Metadata Framework — Silver
✓ Complete
Migration Controller
✓ Complete
IN PROGRESS 6
CI/CD Pipeline Framework
53%
Migration Framework
70%
Governance Framework
40%
Dev / UAT / Prod Setup
60%
Audit Framework
48%
External Sources → SFTP
50%
NOT STARTED 3
Data Quality Framework
Not started
Permissions Framework
Not started
Centralized Framework
Not started

## Slide 6
FRAMEWORK DEVELOPMENT · PHASE TRACKER
Phase-by-phase status for the six in-flight frameworks
TARGET COMPLETION
End of Q3
Complete
In progress
Not started
In review
CI/CD Pipeline Framework
53% complete
Strategy & Governance
50%
Code Packaging & Artifacts
Implement CI
Unit Testing & Coverage
75%
CD to Dev
Promotion Strategy
50%
Release Mgmt & Approvals
Rollback & Recovery
Operationalize
Migration Framework
70% complete
70% overall · per-phase status not individually tracked
Governance Framework
40% complete
Governance Strategy
Metadata & Tagging Model
Policies & Rules
Collibra Integration
Metadata Synchronization
Tag-based Policy Enforcement
in review
Pilot Governance
Operationalize
Dev / UAT / Prod Setup
60% complete
Dev
UAT
80%
Prod
Audit Framework
48% complete
Audit Strategy
Centralized Audit Store
30%
Monitoring & Alerting
60%
Operationalize
External Sources → SFTP
50% complete
SFTP Setup (UAT)
ServiceNow & Data Movement

## Slide 7
02
Business Goal Development
Turning the platform into governed 360° data products for the business
20%
overall complete
4
sub-projects
6
360s on roadmap

## Slide 8
BUSINESS GOAL DEVELOPMENT · PROGRAM BOARD
Archer MVP is delivered; three 360° data builds are now underway
TARGET COMPLETION
End of Q4
4 sub-projects
1 complete
3 in progress
Archer MVP
COMPLETE
100%
Delivered
Credit Admin Risk & Reporting
IN PROGRESS
10%
Target delivery — End of Q3
Customer 360
IN PROGRESS
25%
Target delivery — End of Q4
Account 360
IN PROGRESS
10%
Target delivery — End of Q4

## Slide 9
BUSINESS GOAL DEVELOPMENT · PHASE TRACKER
Phase-by-phase status across the four business-goal sub-projects
TARGET COMPLETION
End of Q4
Complete
In progress
Not started
Archer MVP
3 done · 0 in progress · 3 total
Gather Requirements
Ingest Data to Bronze
Build Dashboard
Credit Admin Risk & Reporting
0 done · 1 in progress · 8 total
Gather Business Requirements
(in progress)
Define KPI Logic & Data Mapping
Ingest Data to Bronze
Transform to Silver
Aggregation / Reporting (Gold)
Build Semantic Layer
Validate & Reconcile
Publish Reports
Customer 360
0 done · 2 in progress · 9 total
Define Strategy & Requirements
(in progress)
Ingest Customer Data to Bronze
(in progress)
Standardize & Cleanse (Silver)
Identity Resolution
Build Customer Clusters
Create Golden Record
Build Facts & Dimensions
Enrich & Build 360 Views
Operationalize
Account 360
0 done · 1 in progress · 7 total
Define Objectives & Scope
(in progress)
Ingest Data to Bronze
Standardize & Cleanse (Silver)
Integrate & Link Data
Build Facts & Dimensions
Build Account-level Views
Operationalize

## Slide 10
03
Business Scope & Value
From hundreds of point reports to six governed 360s on Databricks

## Slide 11
BUSINESS SCOPE · WHO WE SERVE
The business areas and lines of business the platform supports
Production & Revenue
Commercial Sales (Loans) · Small Business · Retail Branch Network · Investments / Brokerage
Operations
Procedures · QC – new accounts · Regulation adherence
Risk Management
BSA / AML · CIP onboarding · Cash transactions · Archer
Credit Administration
Underwriting · Credit review · CECL
Finance
CECL · out of current scope
Audit
Controls & assurance
Marketing
Customer onboarding · campaigns · cross-sell
HR
People & workforce

## Slide 12
CURRENT STATE · HOW WE SUPPORT TODAY
Data reaches the business through raw feeds, portal reports, and the CRM
Data available by
Raw access to daily data
On-demand reports via management portal (Commercial)
Customer-level deposit / loan / fee trending
What the LOBs need
Manage the business with data-driven decisions
Surface info — aggregate · summarize · consolidate sources · layer business rules · trend
Update reporting for regulatory / business changes
CustomerOne (CRM)
Feed it data
Pull referral / opportunity / activity for sales & incentive reporting
Future — SLA reporting on case management

## Slide 13
CURRENT STATE · PAIN POINTS WE'RE SOLVING
Six themes drawn directly from the business and technical assessment
!
Trust & clarity
Accuracy unproven (sentiment exists) · no data dictionary
!
Source confusion
Which source to use? Legacy on-prem EDW vs current Azure Gold
!
Integration & silos
Hard to join data · customer in 4 silos → 1 (Abrigo, CustomerOne, Credit Lens…)
!
Speed to change
2–3 weeks to add fields to EDW, then to Tabular · adding new sources / pipelines is hard
!
Self-service & sprawl
No self-reporting · everyone writes their own Power BI / Excel
!
Scalability
Gold not designed for deep history (2+ yr) → slowness · SSIS & Tabular not scalable · MDS / SCD limits

## Slide 14
BUSINESS SCOPE · AREAS & GROUPING
Scope grouped per the org model, each mapped to the 360° products that serve it
Risk Management
SCOPE
BSA / AML · CIP · cash transactions · Archer · financial crimes (Verafin) · fair lending
SERVED BY
Risk 360
Credit Administration
SCOPE
Underwriting · credit review · CECL · delinquency · watch lists
SERVED BY
Account 360 · Product 360
Business Domains
SCOPE
Customer · accounts · transactions · households · products
SERVED BY
Customer · Account · Transaction · Household · Product 360
Finance
SCOPE
CECL
SERVED BY
Out of current scope
Consumer & Commercial — separate business domains. Built on one shared single source of truth, so the same governed data serves both.

## Slide 15
BUSINESS SCOPE · REPORTING CONSOLIDATION
Hundreds of point reports consolidate into six governed 360° data products
TODAY
SSRS Analytics Portal
Hundreds of point reports · ungoverned · siloed sources
Scorecards
Customer · Digital · Marketing
Loans · Deposits · Payments
Credit Card · Credit Admin
Risk · Financial Crimes · BSA-AML
Investments · Treasury
Incentives · Commissions
➜
consolidate
govern
single source
FUTURE — Six governed 360° data products
1
Customer 360
Customer · Digital · Marketing · Inquiries
2
Account 360
Deposits · Loans · Credit Card
3
Transaction 360
Payments · ACH · fee & balance trending
4
Household 360
Relationships · cross-sell rollups
5
Risk 360
Risk · Financial Crimes · BSA-AML · Fair Lending
6
Product 360
Product mix · portfolio · Credit Admin

## Slide 16
FUTURE-STATE ARCHITECTURE · ENTERPRISE LAKEHOUSE
A single Databricks lakehouse from source systems to business-ready consumption
ORCHESTRATED END-TO-END WITH LAKEFLOW JOBS
DATA SOURCES
CustomerOne · Verafin
Credit Lens · Abrigo
Encompass · Zelle · NCDD
Core banking · EDW
Actimize (retiring)
➜
INGEST
Batch ingestion
CDC ingestion
Streaming ingestion
➜
MEDALLION
Bronze — raw
Silver — cleansed
Gold — 360 products
➜
SERVE
Databricks SQL
AI/BI Genie
Predict · ML lifecycle
➜
CONSUME
BI dashboards
Intelligent apps
Delta Sharing · LOBs
LAKEHOUSE FOUNDATION
Unity Catalog · Delta Lake · Photon · Apache Spark · ADLS
GOVERNANCE
Collibra + Unity Catalog — policy & compliance · lineage · stewardship · business glossary
PLATFORM
Microsoft Azure — Entra · Azure DevOps & GitHub · Key Vault · Monitor · Defender for Cloud

## Slide 17
FUTURE-STATE ARCHITECTURE · AGENTIC CONSUMPTION
Domain Genies put governed 360° data in every user's hands through natural language
FUTURE STATE
QUESTION SOURCES
Chat UI
Apps / Web apps
API clients
Identity (SSO)
Routing Supervisor Agent — Agent Bricks Supervisor + Custom MCP
Customer
Genie
↔ Customer 360
Transaction
Genie
↔ Transaction 360
Risk
Genie
↔ Risk 360
Market
Genie
Compliance
Genie
Shared Semantic Layer — Unity Catalog metric views
GOVERNED LAKEHOUSE DATA
Bronze · Silver · Gold · Summary · Unstructured · External data
UNIFIED, OPEN, GOVERNED LAKEHOUSE FOUNDATION
Governance & Identity: Collibra & Unity Catalog · RBAC/ABAC · policy-as-code Open Storage: Delta Lake · Parquet · flat files · CSV
▼
▼
CONSUMERS / OUTPUTS
Business Users
BI Reporting
External Apps
Operational DBs
Audit Trail
Cost & Quotas

## Slide 18
BUSINESS GOAL DEVELOPMENT · 360° ROADMAP
Six data products, built in sequence, each unlocking use cases and retiring pain
Built on the frameworks already delivered · Customer & Account 360 target end of Q4 · remainder sequenced
1
Customer 360
UNLOCKS
Single customer view · sales & incentive (CustomerOne) · inquiries
Solves: 4 silos → 1 customer
2
Account 360
UNLOCKS
Deposit / loan / credit-card account & portfolio reporting
Solves: EDW vs Gold source confusion
3
Transaction 360
UNLOCKS
Deposit / loan / fee trending · payments · ACH
Solves: deep-history (2+ yr) performance
4
Household 360
UNLOCKS
Relationship & cross-sell · household rollups (Marketing)
Solves: fragmented relationship view
5
Risk 360
UNLOCKS
Tolerance monitoring & breach forecasting (Archer) · Verafin BSA-AML · fair lending
Solves: reactive → proactive · Actimize retired
6
Product 360
UNLOCKS
Product mix · pricing · Credit Administration
Solves: product view · self-service via Genie

## Slide 19
PLATFORM · WHY DATABRICKS
Each platform capability retires a specific, documented pain point
Unity Catalog + Collibra
governance, lineage & a real data dictionary
Genie self-service (natural language)
replaces ad-hoc Power BI / Excel; true self-reporting
Medallion on Delta Lake
one governed source of truth; 4 silos → 1
Photon performance
fast deep-history (2+ yr) & complex queries
Metadata-driven onboarding
shrinks the 2–3 week field / source cycle
Platform rationalization
retire SSIS · Tabular · SSRS portal · Actimize
AI / ML & GenAI foundations
forecasting, propensity, anomaly detection
Scalable lakehouse compute
grows with the data; future-proof

## Slide 20
VALUE · BUSINESS OUTCOMES
Documented problems, the Databricks solution, and the outcome for the business
Archer — proactive risk management, not reactive reporting
A single pane for risk & compliance stakeholders to monitor whether risk metrics are within tolerance, spot deteriorating trends, and forecast where breaches are likely.
PROBLEM
DATABRICKS SOLUTION
OUTCOME
Accuracy unproven; no dictionary
Unity Catalog + Collibra governance
Numbers stakeholders can trust
EDW vs Azure Gold confusion
Medallion single source of truth
One sanctioned source of truth
Customer in 4 silos
Customer / Household 360 identity resolution
One customer, not four
2–3 wk field changes; no self-service
Metadata onboarding + Genie
Faster changes, governed self-service
SSIS / Tabular / Gold not scalable
Databricks lakehouse + Photon
Scalable, performant platform

## Slide 21
DELIVERY · PRIORITIES, CAPACITY & ACCELERATION
Where focus sits today — and what more people would unlock
Current priorities
Top 2–3 priorities — to be confirmed with the team
Capacity today
Current team size, composition & where the bottleneck sits — to be confirmed
Acceleration with more people
e.g. +N engineers → pull Customer / Account 360 forward (illustrative until confirmed)
Placeholder — to be completed after the priorities & capacity discussion.